## Index
Update Date | Version | Description | Name
2020-03-20 | V1.0 | Initial | Cong Shang

## Matrix
Requirement tracking matrix
Requirement NO. | Role | Model | Function | State | Priority level (1-5) | Source Of Requirment | Developer | Tester | Go-live
1.1 | User | Goods display | Main page goods display | finish | Highest | Zoe | Cong | Guozhi Yin | Yes
1.2 |  |  | goods display by categroy | finish | Critical | Zoe | Cong | Guozhi Yin | Yes
1.3 |  |  | view the detail of the goods. | finish | Highest | Zoe | Cong | Guozhi Yin | Yes
2.1 |  | User management | login | finish | Highest | Zoe | Cong | Guozhi Yin | Yes
2.2 |  |  | logout | finish | Medium | Zoe | Cong | Guozhi Yin | Yes
2.3 |  |  | regiest | finish | Critical | Zoe | Cong | Guozhi Yin | Yes
2.4 |  |  | password recover | finish | Medium | Ian | Cong | Guozhi Yin | Yes
2.5 |  |  | view the personal information | finish | Low | Zoe | Cong | Guozhi Yin | Yes
2.6 |  |  | edit the personal information | finish | Low | Zoe | Cong | Guozhi Yin | Yes
3.1 |  | Auction | acution | finish | Highest | Zoe | Cong | Guozhi Yin | Yes
3.2 |  |  | acution | cancel | Highest | Zoe | Cong | Guozhi Yin | NO
4.1 |  | Order management | view the order | finish | Critical | Zoe | Cong | Guozhi Yin | Yes
4.2 |  |  | make appointments | finish | Critical | Micheal | Cong | Guozhi Yin | Yes
5.1 |  | Cart | add items into the cart | finish | Medium | Cong | Cong | Guozhi Yin | Yes
5.2 |  |  | view the cart. | finish | Medium | Cong | Cong | Guozhi Yin | Yes
5.3 |  |  | delete items form cart | finish | Low | Micheal | Cong | Guozhi Yin | Yes
6.1 |  | About us | About us | finish | Highest | Zoe | Cong | Guozhi Yin | Yes
7.1 |  | Contact us | Contact us | finish | Highest | Zoe | Cong | Guozhi Yin | Yes
8.1 | admin | Goods managemet | Display product list | finish | Critical | Zoe | Cong | Guozhi Yin | Yes
8.2 |  |  | add a new commodity | finish | Highest | Zoe | Cong | Guozhi Yin | Yes
8.3 |  |  | edit the commodity | finish | Highest | Zoe | Cong | Guozhi Yin | Yes
8.4 |  |  | change the commodity state | finish | Medium | Zoe | Cong | Guozhi Yin | Yes
9.1 |  | User management | display user list | finish | Highest | Zoe | Cong | Guozhi Yin | Yes
9.2 |  |  | change the user's state | finish | Low | Cong | Cong | Guozhi Yin | Yes
10.1 |  | Order management | display order list | finish | Highest | Cong | Cong | Guozhi Yin | Yes
10.2 |  |  | change the order list state | finish | Medium | Cong | Cong | Guozhi Yin | Yes
11.1 | System | generate orders | generate orders | finish | Highest | Cong | Cong | Guozhi Yin | Yes

## requirement description
No. | Model | Model | functional point | description
1.1 | User | Goods display | Main page goods display | display the 12 goods which are the closest to the close time
1.2 |  |  | goods display by category | show the goods by category. In this system, it splits into 5 categories, such as toy, kitchen, tools, decoration and clothes.
1.3 |  |  | view the detail of the goods. | display the product details in the web page which include the title, initial price, current price, the picture, the description of goods, close date and bid history
2.1 |  | User management | login | user-input user name and password to login to the website, if the user did not login, the user only can browse the goods， but do not allow to bid.
2.2 |  |  | logout | user can log out at any time, if users do not do anything than 30 minutes, the system will log out automatically
2.3 |  |  | register | New users can register as members. Requires user names to be unique and can not be duplicated with existing user names.
2.4 |  |  | password recover | A user matches a mail address or phone number with a username. When the match is successful, the user can reset the password.
2.5 |  |  | view the personal information | show the user's personal information on the page.
2.6 |  |  | edit the personal information | user can update their personal information, but the user name could not be updated.
3.1 |  | Auction | auction | the bids price must higher than the current price. The auction must be easy than the close date.
3.2 |  |  | donation | this function has been deleted.
4.1 |  | Order management | view the order | after the user login, user can check their order which they win.
4.2 |  |  | make appointments | select a date to pick up and leave a message to the store.
5.1 |  | Cart | add items into the cart | Users can save items of interest to them in shopping carts
5.2 |  |  | view the cart. | show the state of items which is in the user's cart.
5.3 |  |  | delete items form cart | delete commodities from their cart.
6.1 |  | About us | About us | show the introduction of the online store.
7.1 |  | Contact us | Contact us | shows the information about the shop. It includes address, website, contact phone number.
8.1 | Admin | Goods management | Display product list | in the model，the system displays all of the goods in the system.
8.2 |  |  | add a new commodity | Administrators can add new commodities. The default commodity status is on sale。The close date of the newly uploaded commodity must not be less than the current system date
8.3 |  |  | edit the commodity | If the commodity has already been bided， the price can not be modified.
8.4 |  |  | change the commodity state | the administrator can delete the item on sale when the item status is selling. After deletion, users can not see commodity in the manpage
9.1 |  | User management | display user list | show all of the users in the list
9.2 |  |  | change the user's state | the administrator can change the state of users. When the user state is changed to disable, the user could not log in
10.1 |  | Order management | display order list | show all the orders in the list.
10.2 |  |  | change the order list | when the user picks up, the admin changes the order state to finish.
11.1 | System | generate orders | generate orders | When the end date of the item is greater than the system date, the system automatically generates the order. Winners and administrators can view order details.