## Sheet1
Milestone list.
No. | Milestones | Date | Events | Deliverable
1 | Initiation | 2020-03-23 | Advisors and clients accept project team proposal | project proposal
2 | Design | 2020-03-30 | Complete project design review, including page design, database design process design, system structure design. | System Analysis and Design document
3 | Development | 2020-05-15 | Complete code writing and unit testing. Code quality reviewed | Project source code
4 | Testing | 2020-05-26 | Complete integration test, system test, and acceptance test. Client satisfy the user acceptance test. | testing plan, test cases and test reports
5 | Client handover | 2020-05-29 | Support the project go live and finish the client training | Submit the user manuals, installation manuals and training material