## Sheet3
WBS | Task description | Duration | Start | Finish | Predecessors | responsible person | deliverable | Quality requirements | Cost
1 | Initiation | 5 days | Mon 02/03/20 | Fri 06/03/20
1.1 | Analyze the list of projects and find a suitable project | 1 day | Mon 02/03/20 | Mon 02/03/20 |  | Cong,Michael | List of potential projects
1.2 | System analysis(include risk analysis, technical analysis and feasibility analysis) | 1 day | Tue 03/03/20 | Tue 03/03/20 | 2 | Michael | feasibility analysis result
1.3 | getting the frist version of the requirment form client | 2 days | Wed 04/03/20 | Thu 05/03/20 | 3 | Client,Cong,Michael
1.4 | Prepare the Project Bid document | 1 day | Fri 06/03/20 | Fri 06/03/20 | 4 | Michael
2 | Plannig | 10.5 days | Mon 09/03/20 | Mon 23/03/20 | 1
2.1 | requriment management | 5 days | Mon 09/03/20 | Fri 13/03/20
2.1.1 | collect requirments from client | 0.5 days | Mon 09/03/20 | Mon 09/03/20 | 5 | Michael
2.1.2 | make prototype | 4 days | Mon 09/03/20 | Fri 13/03/20 | 8 | Michael
2.1.3 | confirm the requirements | 0.5 days | Fri 13/03/20 | Fri 13/03/20 | 9 | Michael
2.2 | Scope Management | 3 days | Mon 09/03/20 | Thu 12/03/20
2.2.1 | Scope statement | 1 day | Mon 09/03/20 | Tue 10/03/20 | 8 | Cong
2.2.2 | WBS and WBS dictionary | 2 days | Tue 10/03/20 | Thu 12/03/20 | 12 | Cong
2.3 | schedule management | 2 days | Thu 12/03/20 | Mon 16/03/20 | 11
2.3.1 | Estimate | 4 hrs | Thu 12/03/20 | Thu 12/03/20 | 13 | Cong
2.3.2 | Make a detail schedule | 1.5 days | Fri 13/03/20 | Mon 16/03/20 | 15 | Cong
2.4 | communication management | 7 days | Mon 09/03/20 | Tue 17/03/20
2.4.1 | Indentify and register stakeholders | 4 hrs | Mon 09/03/20 | Mon 09/03/20 | 1 | Cong
2.4.2 | make the communication plan | 4 hrs | Mon 16/03/20 | Mon 16/03/20 | 18,7 | Michael
2.4.3 | Making training plan | 4 hrs | Tue 17/03/20 | Tue 17/03/20 | 21 | Michael
2.5 | Human resource management | 1 day | Mon 16/03/20 | Tue 17/03/20 | 7
2.5.1 | Write CV | 4 hrs | Mon 16/03/20 | Mon 16/03/20 | 19,16 | Cong,Michael
2.5.2 | Prepare the team agreement | 4 hrs | Tue 17/03/20 | Tue 17/03/20 | 22 | Michael
2.6 | Prepare Proposal Document | 4.5 days | Tue 17/03/20 | Mon 23/03/20
2.6.1 | project background intrudction and management method description | 2.5 days | Wed 18/03/20 | Fri 20/03/20 | 20 | Michael
2.6.2 | write project mandate | 1 day | Fri 20/03/20 | Mon 23/03/20 | 25 | Michael
2.6.3 | Methodology and technical analysis | 2 days | Tue 17/03/20 | Wed 18/03/20 | 22 | Cong
2.6.4 | Meeting with advisor and getting approval form the turtor | 4 hrs | Mon 23/03/20 | Mon 23/03/20 | 25,27 | Cong,Robert ,Michael
3 | Execution | 49.5 days | Mon 23/03/20 | Fri 29/05/20 | 6
3.1 | System analysis and desgin | 6.5 days | Mon 23/03/20 | Tue 31/03/20
3.1.1 | use case design | 4 hrs | Mon 23/03/20 | Mon 23/03/20 | 6 | Cong
3.1.2 | structure design | 4 hrs | Tue 24/03/20 | Tue 24/03/20 | 31 | Cong
3.1.3 | flow-process diagram | 4 hrs | Tue 24/03/20 | Tue 24/03/20 | 32 | Cong
3.1.4 | database design | 1 day | Tue 24/03/20 | Wed 25/03/20 | 28,32 | Michael
3.1.5 | flow-process analysis | 1 day | Wed 25/03/20 | Thu 26/03/20 | 34 | Michael
3.1.6 | Write desgin document | 2 days | Thu 26/03/20 | Mon 30/03/20 | 35 | Michael
3.1.7 | Review the system desgin | 4 hrs | Mon 30/03/20 | Mon 30/03/20 | 36 | Michael,Cong,Ian
3.1.8 | Requirements Analysis -problems identified, possible solutions | 1 day | Tue 31/03/20 | Tue 31/03/20 | 37 | Michael
3.2 | Develop | 31 days | Wed 01/04/20 | Wed 13/05/20 | 30
3.2.1 | build development environment | 2 days | Wed 01/04/20 | Thu 02/04/20 | 37 | Cong
3.2.2 | set up project structure | 2 days | Fri 03/04/20 | Mon 06/04/20 | 40 | Cong
3.2.3 | Goods display | 6 days | Tue 07/04/20 | Tue 14/04/20
3.2.3.1 | Main page goods display | 2 days | Tue 07/04/20 | Wed 08/04/20 | 41 | Cong
3.2.3.2 | goods display by categroy | 1 day | Thu 09/04/20 | Thu 09/04/20 | 43 | Cong
3.2.3.3 | view the detail of the goods. | 1 day | Fri 10/04/20 | Fri 10/04/20 | 44 | Cong
3.2.3.4 | Auction | 2 days | Mon 13/04/20 | Tue 14/04/20 | 45 | Cong
3.2.4 | User management | 3 days | Wed 15/04/20 | Fri 17/04/20 | 42
3.2.4.1 | login | 4 hrs | Wed 15/04/20 | Wed 15/04/20 | 42 | Cong
3.2.4.2 | logout | 4 hrs | Wed 15/04/20 | Wed 15/04/20 | 48 | Cong
3.2.4.3 | regiest | 4 hrs | Thu 16/04/20 | Thu 16/04/20 | 49 | Cong
3.2.4.4 | password recover | 4 hrs | Thu 16/04/20 | Thu 16/04/20 | 50 | Cong
3.2.4.5 | view the personal information | 4 hrs | Fri 17/04/20 | Fri 17/04/20 | 51 | Cong
3.2.4.6 | edit the personal information | 4 hrs | Fri 17/04/20 | Fri 17/04/20 | 52 | Cong
3.2.5 | Order management | 2 days | Mon 20/04/20 | Tue 21/04/20 | 47
3.2.5.1 | view the order | 1 day | Mon 20/04/20 | Mon 20/04/20 | 46 | Cong
3.2.5.2 | make appointments | 1 day | Tue 21/04/20 | Tue 21/04/20 | 55 | Cong
3.2.6 | Cart management | 2 days | Wed 22/04/20 | Thu 23/04/20
3.2.6.1 | add items into the cart | 1 day | Wed 22/04/20 | Wed 22/04/20 | 54 | Cong
3.2.6.2 | delete item form the cart | 1 day | Thu 23/04/20 | Thu 23/04/20 | 58
3.2.6.3 | view the cart. | 1 day | Thu 23/04/20 | Thu 23/04/20 | 58 | Cong
3.2.7 | Goods managemet（admin） | 3 days | Fri 24/04/20 | Tue 28/04/20
3.2.7.1 | Display product list | 1 day | Fri 24/04/20 | Fri 24/04/20 | 57 | Cong
3.2.7.2 | Add a new commodity | 1 day | Mon 27/04/20 | Mon 27/04/20 | 62 | Cong
3.2.7.3 | Edit the commodity | 4 hrs | Tue 28/04/20 | Tue 28/04/20 | 63 | Cong
3.2.7.4 | Change the commodity state | 4 hrs | Tue 28/04/20 | Tue 28/04/20 | 64 | Cong
3.2.8 | User management （admin） | 2 days | Wed 29/04/20 | Thu 30/04/20
3.2.8.1 | display user list | 1 day | Wed 29/04/20 | Wed 29/04/20 | 61 | Cong
3.2.8.2 | change the user's state | 4 hrs | Thu 30/04/20 | Thu 30/04/20 | 67 | Cong
3.2.8.3 | reset the password | 4 hrs | Thu 30/04/20 | Thu 30/04/20 | 68 | Cong
3.2.9 | Generate orders automatically | 2 days | Fri 01/05/20 | Mon 04/05/20
3.2.9.1 | display order list | 1 day | Fri 01/05/20 | Fri 01/05/20 | 66 | Cong
3.2.9.2 | change the order list | 1 day | Mon 04/05/20 | Mon 04/05/20 | 71 | Cong
3.2.10 | Page beautification | 6 days | Tue 05/05/20 | Tue 12/05/20
3.2.10.1 | Page beautification | 2 days | Tue 05/05/20 | Wed 06/05/20 | 70 | Cong
3.2.10.2 | About us Page | 4 hrs | Thu 07/05/20 | Thu 07/05/20 | 74 | Cong
3.2.10.3 | Contact us Page | 4 hrs | Thu 07/05/20 | Thu 07/05/20 | 75 | Cong
3.2.10.4 | Buffer time | 3 days | Fri 08/05/20 | Tue 12/05/20 | 76
3.2.11 | Code review | 1 day | Wed 13/05/20 | Wed 13/05/20 | 77 | Cong
3.3 | Testing | 40 days | Wed 01/04/20 | Tue 26/05/20
3.3.1 | Prepare the testing enviroment | 1 day | Thu 14/05/20 | Thu 14/05/20 | 39 | Michael,Cong
3.3.2 | integration testing | 34 days | Wed 01/04/20 | Mon 18/05/20
3.3.2.1 | write testing plan | 4 hrs | Wed 01/04/20 | Wed 01/04/20 | 30 | Michael
3.3.2.2 | Prepare test cases | 1 day | Wed 01/04/20 | Thu 02/04/20 | 82 | Michael
3.3.2.3 | execute integration testing | 1 day | Fri 15/05/20 | Fri 15/05/20 | 83,80 | Michael
3.3.2.4 | fix problems | 1 day | Mon 18/05/20 | Mon 18/05/20 | 84 | Cong
3.3.2.5 | Write the intergration testing report | 4 hrs | Mon 18/05/20 | Mon 18/05/20 | 84 | Michael
3.3.3 | System testing | 34.5 days | Thu 02/04/20 | Wed 20/05/20
3.3.3.1 | Prepare test cases | 1 day | Thu 02/04/20 | Fri 03/04/20 | 83 | Michael
3.3.3.2 | execute system testing | 1 day | Tue 19/05/20 | Tue 19/05/20 | 88,81 | Michael
3.3.3.3 | fix problems | 1 day | Wed 20/05/20 | Wed 20/05/20 | 89 | Cong
3.3.3.4 | Write the intergration testing report | 1 day | Wed 20/05/20 | Wed 20/05/20 | 89 | Michael
3.3.4 | Acceptance testing | 8 days | Fri 15/05/20 | Tue 26/05/20
3.3.4.1 | Prepare the testing enviroment | 1 day | Thu 21/05/20 | Thu 21/05/20 | 87 | Client,Cong,Michael
3.3.4.2 | Prepare test cases | 1 day | Fri 15/05/20 | Fri 15/05/20 | 80 | Client
3.3.4.3 | Perform Acceptance Testing | 1 day | Fri 22/05/20 | Fri 22/05/20 | 94,93 | Client
3.3.4.4 | fix problems | 1 day | Mon 25/05/20 | Mon 25/05/20 | 95 | Cong
3.3.4.5 | Confirmed the problem has been fixed | 4 hrs | Tue 26/05/20 | Tue 26/05/20 | 96 | Client
3.3.4.6 | Write the acceptance testing report | 4 hrs | Tue 26/05/20 | Tue 26/05/20 | 97 | Client
3.4 | Go-Live | 38.5 days | Fri 03/04/20 | Wed 27/05/20
3.4.1 | Go-live plan | 4 hrs | Fri 03/04/20 | Fri 03/04/20 | 88 | Michael
3.4.2 | Installation Manual | 1 day | Mon 06/04/20 | Mon 06/04/20 | 100 | Michael
3.4.3 | prepare the enviroment | 1 day | Mon 18/05/20 | Mon 18/05/20 | 80,94 | Client
3.4.4 | go-live enviroment check | 4 hrs | Wed 27/05/20 | Wed 27/05/20 | 102,92 | Cong,Michael
3.4.5 | Support go-live（implementing） | 4 hrs | Wed 27/05/20 | Wed 27/05/20 | 103 | Client,Cong,Michael
3.5 | maintenance | 5 days | Mon 25/05/20 | Fri 29/05/20
3.5.1 | Support | 1 day | Thu 28/05/20 | Thu 28/05/20 | 104 | Cong,Michael
3.5.2 | User guide book | 1 day | Mon 25/05/20 | Mon 25/05/20 | 95 | Michael
3.5.3 | Help documents | 4 hrs | Tue 26/05/20 | Tue 26/05/20 | 107 | Michael
3.5.4 | Wirte training material | 4 hrs | Fri 29/05/20 | Fri 29/05/20 | 101106 | Michael
3.5.5 | Training Clinet | 4 hrs | Fri 29/05/20 | Fri 29/05/20 | 109 | Michael
4 | Monitoring | 68 days | Wed 04/03/20 | Sat 06/06/20
5 | Closing | 6 days | Mon 01/06/20 | Mon 08/06/20 | 105
5.1 | Gaining stakeholder and customer acceptance | 1 day | Mon 01/06/20 | Mon 01/06/20 | 105 | Client
5.2 | Client feedback report | 1 day | Tue 02/06/20 | Tue 02/06/20 | 166 | Client
5.3 | Summary the lessons-learned and write a report（include closeout report） | 1 day | Tue 02/06/20 | Tue 02/06/20 | 166 | Michael
5.4 | Advisor Report | 4 hrs | Mon 01/06/20 | Mon 01/06/20 |  | Ian
5.5 | Archving project files | 4 hrs | Wed 03/06/20 | Wed 03/06/20 | 168 | Michael
5.6 | Submint the organizational process assets | 4 hrs | Wed 03/06/20 | Wed 03/06/20 | 170 | Michael
5.7 | perpare the final presentation | 2 days | Thu 04/06/20 | Fri 05/06/20 | 171 | Michael,Cong
5.8 | perpare the panel interview | 1 day | Mon 08/06/20 | Mon 08/06/20 | 172 | Cong,Michael