## hidden (hidden)
2020-03-02 | 2020-03-08 | 2 March 2020---8 March 2020
2020-03-09 | 2020-03-15 | 9 March 2020---15 March 2020
2020-03-16 | 2020-03-22 | 16 March 2020---22 March 2020
2020-03-23 | 2020-03-29 | 23 March 2020---29 March 2020
2020-03-30 | 2020-04-05 | 30 March 2020---5 April 2020
2020-04-06 | 2020-04-12 | 6 April 2020---12 April 2020
2020-04-13 | 2020-04-19 | 13 April 2020---19 April 2020
2020-04-20 | 2020-04-26 | 20 April 2020---26 April 2020
2020-04-27 | 2020-05-03 | 27 April 2020---3 May 2020
2020-05-04 | 2020-05-10 | 4 May 2020---10 May 2020
2020-05-11 | 2020-05-17 | 11 May 2020---17 May 2020
2020-05-18 | 2020-05-24 | 18 May 2020---24 May 2020
2020-05-25 | 2020-05-31 | 25 May 2020---31 May 2020
2020-06-01 | 2020-06-07 | 1 June 2020---7 June 2020
2020-06-08 | 2020-06-14 | 8 June 2020---14 June 2020
2020-06-15 | 2020-06-21 | 15 June 2020---21 June 2020
2020-06-22 | 2020-06-28 | 22 June 2020---28 June 2020
2020-06-29 | 2020-07-05 | 29 June 2020---5 July 2020
2020-07-06 | 2020-07-12 | 6 July 2020---12 July 2020
2020-07-13 | 2020-07-19 | 13 July 2020---19 July 2020
2020-07-20 | 2020-07-26 | 20 July 2020---26 July 2020

## individual log (hidden)
Day | Date | Task | Task Description | Begin Time | End Time | Total Work Hours
2 March 2020---8 March 2020
1 | 2020-03-02 | Using brainstorming analyze all of projects and try to find a suitable project. | Using brainstorming methods analyze the list of projects and try to find a suitable project. However, we found all of the projects not suitable for us. The only project which can be considered is commodity price comparison items. After contracting with the client, they demand is to develop a mobile application. we don't have mobile app development and web crawler development experience, so the technical risk is very high. finally, we have to abandoned this project. | 10:00 | 18:00 | 8
2 | 2020-03-03 | Client Meeting |  |  |  | 1
3 | 2020-03-04 | contact with our client and try to find a project opportunity | We find a client who name is Zoë. She will provide us some project opportunities. In the beginning, we advise our custom to build a online store to sell them all the goods. Client suggests that it was impossible because every good is unique. They do not have energy to upload everything to the online store. After discussion, the client decided to build a auction system. | 10:00 | 18:00 | 8
4 | 2020-03-05 | get the first version of the requirement from the client. | Getting the first version of the requirement form our client. We discussed the requirement. We pointed out this system should have two type user，normal user and administrator, and should divide to online shop site and management site. | 9:00 | 17:00 | 8
5 | 2020-03-06
6 | 2020-03-07 | Team meeting |  |  |  | 2
9 March 2020---15 March 2020 |  |  |  |  | Total | 27
1 | 2020-03-09 | Estimate the workload. | We have already got clear requirements from our client. Beas on the confirmed requirements, I estimated the workload. Because of a lot of unsure things in this step, I only estimate it by my experience. | 10:00 | 14:00 | 4
2 | 2020-03-10 | Make the schedule plan and client meeting | After estimate the workload， I began using Microsoft Project to detail the project schedule plan. The method is that, firstly, I identify all the milestones， because the time of the project is fixed. Secondly, I allocate the first level of work based on the results of the estimated workload. | 10:00 | 18:00 | 9
3 | 2020-03-11 | Make the schedule plan and prepare the scope statement document. | 1. Detail the project schedule plan. 2. Define the scope of the project. Identify what is not part of the project and write it in a document. | 10:00 | 14:00 | 8
4 | 2020-03-12 | Write the project scope statement and refine the project schedule plan into work packages. | 1. Finish the scope statement document. 2. Prepare the work breakdown structure (WBS) of this project Continue refining the project schedule plan into work packages. | 14:00 | 18:00 | 8
5 | 2020-03-13 | Refine the work package of the project and sort the tasks. | Refine the work package of the project and sort the tasks. | 10:00 | 18:00 | 8
6 | 2020-03-14 | Team meeting |  |  |  | 2
27 April 2020---3 May 2020 |  |  |  |  | Total | 39
1 | 2020-03-16 | Update the schedule plan and identify stakeholders of this project.,Advisor meeting | 1. Optimize the work content. And adjust the work content. 2. Identify project stakeholders and record them in the stakeholder register |  |  | 9
2 | 2020-03-17 | Prepare Personal CV and write the communication plan. Client meeting | 1. Make the communication plan and write it in a document. 2. Prepare the personal CV. |  |  | 9
3 | 2020-03-18 | Prepare the proposal document. Focus on the methodologies of development and technical product. | 1.Research methodologies of development. Compare the main of the methodologies. Such as Waterfall, rapid application, agile, prototyping. 2.compair the popular databases in the world, and choose one of them for this project. I chose MySQL because it is free and easy to use. |  |  | 8
4 | 2020-03-19 | Feasibility analysis，analysis of resources requirements and prepare client acceptance agreement | 1. Feasibility analysis of the project in aspects of finance, time, technology and market 2. Analysis of resources requirements for the project 3. Prepare client acceptance agreement |  |  | 8
5 | 2020-03-20
6 | 2020-03-21 | Team meeting |  |  |  | 2
23 March 2020---29 March 2020 |  |  |  |  | Total | 36
1 | 2020-03-23 | ,Advisor meeting |  |  |  | 1
2 | 2020-03-24 | Draw the use case diagram. | 1. Meeting with an advisor, review our proposal document 2. Design the system. Design use case diagram using visor according to user requirements |  |  | 8
3 | 2020-03-25 | Draw the system frameworks diagram and business flow- process diagram | 1. System structure design. Draw a system structure diagram. 2. Draw business flow process diagram depends on the use of requirement. |  |  | 8
4 | 2020-03-26 | Draw business flow- process diagram | Draw business flow process diagram. A total of 12 business flow diagram were drawn. |  |  | 4
5 | 2020-03-27
6 | 2020-03-28 | Team meeting |  |  |  | 2
30 March 2020---5 April 2020 |  |  |  |  | Total | 23
1 | 2020-03-30
2 | 2020-03-31 | Review the system design, client meeting | Review the system design and update incorrect content |  |  | 5
3 | 2020-04-01 | Prepare the development environment. | Prepare development envrioment. Installation of development tools, including JDK ，Eclipse， MySQL. Experience: I tried to use IntelliJ IDEA to develop, but I give up. The reason is that even if the IntelliJ IEDA provides lots of useful function, I do not have enough time to learn how to use it, because its layout and shortcut key is completely different from eclipse. |  |  | 8
4 | 2020-04-02 | Build development envrioment. | Prepare development envrioment. I got a lot of problems during the installation installing the MySQL database. 1. When I install the MySQL, it prompted that the system was missing Microsoft visual C++, so it did not meet the installation requirements. 2. As the first problem, the installation process prompts that the system misses Python. However, I installed all of the required software, but I still could not install all products of MySQL 8 into my laptop. In the end, I only had to install the server of MySQL database. |  |  | 8
5 | 2020-04-03 | set up technical frameworks of the project. | The first step, I analyzed the more popular technical frameworks such as Struts, JSP，Spring MVC, Hibernate, MyBatis and so on. I used to use these products before, but I have forgotten how to use. Next step, I try to find some free frameworks form the internet. However, I could not find a satisfactory framework. finally，I decided to use basic technology. JSP +Servlet. |  |  | 8
6 | 2020-04-04 | Team meeting |  |  |  | 2
6 April 2020---12 April 2020 |  |  |  |  | Total | 31
1 | 2020-04-06 | Verify that this framework is usable | 1.Using the JDBC test the database connection. 2. Try to write a demo code to prove that this framework is usable |  |  | 8
2 | 2020-04-07 | Develop the main page of this system and client meeting | 1.Import the front page template into my project. 2. Adjust the layout of the page according to the prototype. 3. Separate the top and bottom of the page into a separate JSP file. |  |  | 9
3 | 2020-04-08 | Show Goods on the main page. | At this moment, there is no commodity data in the database, I inserted some fake commodities data into the database for testing. According to the requirement document, the main page will display 12 goods nearest to the closing time. The problem on this page is that the size of a commodity picture affects the layout of the page. The solution is that I use CSS to picture showing in the fixed size. |  |  | 8
4 | 2020-04-09 | Goods display by category. | In this project, it has five different categories. We use five menus to display different goods. |  |  | 8
5 | 2020-04-10 | display the detailed information about the goods | Using one-page display the commodity information. The challenge of this function is the countdown tools. I use javascript to judge how long will the commodity close. |  |  | 8
6 | 2020-04-11 | Team meeting |  |  |  | 2
13 April 2020---19 April 2020 |  |  |  |  | Total | 43
1 | 2020-04-13 | develop the auction function. | The function of commodity auction is the core of an auction website. It's also a very challenging job. The biggest problem is that the system does not know when to end the auction. After thinking, there are two solutions: 1. when the system starts, the system loads all product information into the memory. Use the close time of commodities in memory and the system time to match continuously, if the match reaches the close time, the commodity will stop the auction and generates an order. The advantage of this scheme is that it can control the close time of the auction very accurately. The disadvantages are: the development is very difficult and the workload is large. The first step is to load all commodities information into memory during the system startup phase, and start a separate thread for monitoring the time. Another difficulty is to ensure that the data in memory must be consistent with the database. When adding a new commodity or modifying or deleting commodities, the system needs to synchronize the data with memory. 2. When the user views the goods, firstly the system will check whether the goods have exceeded the end time or when the goods reach at the end time. The system uses Ajax technology to trigger the order generating program. The advantage of this scheme is easy to achieve. The disadvantage is that order information is not generated in real-time. Considering that there is no statistical function in this project, so we chose the second scheme |  |  | 8 | 商品拍卖功能是拍卖网站的核心。也是一个非常有技术挑战的工作。 我们遇到的最大问题是系统无法判断何时结束订单。 思考后，共有两种解决方法： 1.在系统启动后，将所有商品信息加载到系统内存中。利用内存中的商品结束时间与系统的时间不断的匹配，如果匹配成功，则商品停止拍卖并生成订单。 这个方案的优点是：非常准确的能控制商品的拍卖结束日期。 缺点是：开发难度很大，工作量大。首先要在系统启动阶段加载所有商品到内存，并启用一个独立线程进行日期的监控。另外的一个难度是需要保证内存中的数据与数据库中的商品数据一致。当新增商品或修改，删除商品时，则需要同步内存中的数据。 2.在查看商品时候，首先判断商品是否已经超过了结束时间或者在商品到达结束时间的时候。AJAX技术触发生成订单的程序。 这个方案的好处是容易实现。 坏处是订单信息不是实时生成的。 考虑到本项目没有统计功能，因此选择了第二种方案。
2 | 2020-04-14 | develop the user login and logout function | Develop the user login and logout function 1. The original plan is to continue to develop the auction function today, but the system must record user information before bidding. Therefore, the user management function is developed in advance. 2. I didn't use a cookie in the login function. in other words, the user must type the user name and password, when they log in the system. 3. If the user does not do anything in 15 minutes, the user needs to log in again |  |  | 8 | 我并没有利用cookie在用户的登录的时候,
3 | 2020-04-15 | develop the auction function. | Keep coding the auction function. the main job of today is when the commodities reach at the end time, the system uses AJAX to call order generation program. |  |  | 8
4 | 2020-04-16 | Develop the user register and password recover function | When a user registers, the user name can not be repeated with the database. if the user name has already been taken, the system will prompt the error message. Password recover function needs the user to type a correct email address or mobile number. If the password or email address is correct, the user can change the password by themselves. |  |  | 8
5 | 2020-04-17 | check or update profile. | Registered Members can check or update their personal information except for the user name |  |  | 8
6 | 2020-04-18 | Team meeting |  |  |  | 2
20 April 2020---26 April 2020 |  |  |  |  | Total | 42
1 | 2020-04-20 | develop viewing the display orders and make an appointment to pick up functions, Advisor meeting | Normal users can only see their orders For customers, they can make an online appointment for pick-up and leave a message after they win the auction. It should be noted that the appointment time must be later than the current time. |  |  | 9 | 用户只能看到自己的订单，管理员可以看到所有人的订单。 对于客户可以在线预约取货时间并留言，需要注意的是预约时间一定要大于当前时间。 管理员可以更改订单的状态，当状态变更为已取货，整个交易流程结束。
2 | 2020-04-21 | develop the cart function | Imitating the function of the Trademe, user can add concerned commodities into the cart. if the user auctioned a commodity， the commodity will be automatically added to the shopping cart. In addition, when adding a commodity to the shopping cart, the system should check whether the goods are already in the shopping cart. If it already exists in the cart, Adding is not allowed. |  |  | 8 | 模仿trademe的功能，用户可以将关注的商品添加的购物车，或者只有用户对某个商品出价拍卖过，则商品自动添加到购物车。 另外商品在添加购物车的时候需要判断商品是否已经在购物车中。如果已经存在于购物车中，则不允许添加。
3 | 2020-04-22 | develop cart management function, client meeting | Users can delete items that they no longer concerned in their shopping cart. The implementation of the code is to set a delete state of the commodity rather than to delete the data from the database. |  |  | 9 | 用户可以在购物车中删除不再关注的商品。代码的实现是将购物车中的商品设置成删除状态，而不是真正的把数据从数据库中删除。
4 | 2020-04-23 | develop commodity management model. | I will use a new template for the management side. The download address of the template is: http://www.cssmoban.com/cssthemes/9300.shtml 1. Separate the menu into a separate JSP file 2. The imported CSS conflicts with the original template. Merge the public content. |  |  | 8 | 后台管理模块新的页面模板。模板的下载地址为：http://www.cssmoban.com/cssthemes/9300.shtml 1.将页面中的菜单分离成单独的jsp文件。 2.导入的CSS与原模板的文件存在冲突。将其公共内容进行合并。
5 | 2020-04-24 | develop adding a new commodity | Develop add a commodity function. The difficulty is uploading pictures. should be noticed that The form format in the page is: enctype = "multipart / form-data" In Servlet, the method of parsing form is different from other Servlets. the system judges the uploaded file, it only supports common image formats. Images uploaded by the system will be renamed. To avoid repetition, I use UUID to get random names. The disadvantage of this method is that it can't be classified by file name. |  |  | 8 | 开发新增商品功能。 难点是上传图片。页面中使用的表单格式为：enctype="multipart/form-data" servlet中，解析表单的方法与其他servlet不同。 在判断上传的文件格式时，只允许上传常见的图片格式。 系统上传的图片会被重新命名。为了避免重复，使用的是UUID方式获取随机的名字。这种方法的坏处是不能按文件名进行分类管理。
6 | 2020-04-25 | Team meeting |  |  |  | 2
27 April 2020---3 May 2020 |  |  |  |  | Total | 44
1 | 2020-04-27 | develop the commodity management model, Advisor meeting | 1 only admin user can modify the commodity information 2. When a commodity has already bid by someone, the starting price cannot be modified 3. If did no select a new picture when modifying the commodity the old picture shall be used. 4. After the status of a commodity is changed to delete, the commodity will not be displayed on the store page. |  |  | 9 | 1只有管理员才能修改商品。 2当已经有人出价拍卖后，商品的起拍价格不能再调整。 3.如果修改商品时候未选择新图片，则保持使用旧的图片。 4.商品的状态修改为删除后，商城中将不在显示。
2 | 2020-04-28 | develop the user management model | DDevelop user management model |  |  | 8 | 开发用户管理模块。
3 | 2020-04-29 | Develop the user management model | Develop the function to modify user status. There are two types of user states. 1. The admin user can set the user to disable. When it is set to disable, the user can no longer log in to the system for any operation. 2. Admin user can set normal users to admin. The admin user role cannot be registered. Only authorized by the admin user. |  |  | 8 | 开发修改用户状态的功能。 用户状态分为两类， 1.管理员可以将用户设置成disable。当被设置成disable后，用户不能再登录系统进行任何操作。 2.管理员可以将普通用户设置成管理员。管理员角色不能被注册，只有管理员可以授权。
4 | 2020-04-30 | Develop the order management model | Admin user can see all of the orders. This display page, I use the same page as my personal order page. The admin user can change the status of the order. When the status changes to picked up, the whole business process will end. |  |  | 8 | Admin user can see all of orders. 这个展示页面，我使用的与个人订单相同的页面。 The admin user can change the status of the order. When the status changes to picked up, the whole business process will be end.
5 | 2020-05-01 | Develop the order management model | Using different colours to distinguish the status of orders. Users can view auction bid history information through page Jump |  |  | 8 | 利用不同颜色区分不同订单的状态。并且在管理界面可以查看拍卖的出价历史记录信息。
6 | 2020-05-02 | Team meeting |  |  |  | 2
4 May 2020---10 May 2020 |  |  |  |  | Total | 43
1 | 2020-05-04 | Page beautification, Advisor meeting | Replace the advertising page and system logo. Unify the system icons Check the page for spelling errors correct the displayed information of the store bottom page. Add commodity search function on the main page. |  |  | 9
2 | 2020-05-05 | Page beautification | Check all prompt information and alert message. Permission validation to ensure that each servlet validates session state. Using JavaScript and HTML5 new characteristic verifies the inputs.such as limit the type, length of the input. Required .etc. |  |  | 8
3 | 2020-05-06 | Page beautification | Maintain the contents of all error prompts and message reminders Adjust the bidding function of the auction. |  |  | 8
4 | 2020-05-07 | Add about us page and contact us page | Use iframe to show Google maps. There is a third party on the Internet to provide Google location information services. After type specific location information, the URL with address information will be automatically generated, |  |  | 8
5 | 2020-05-08
6 | 2020-05-09 | Team meeting |  |  |  | 2
11 May 2020---17 May 2020 |  |  |  |  | Total | 35
1 | 2020-05-11 | Advisor meeting |  |  |  | 1
2 | 2020-05-12
3 | 2020-05-13 | Code review | 1.Optimizing code 2.Delete all unused variables 3.Formatting code 4.Delete annotated code |  |  | 4
4 | 2020-05-14 | prepare the testing environment. | 1.build the test environment on another laptop. 2.the main tasks is that install JDK and database. 3.Package this system to a war file and deploy it in the test environment |  |  | 8
5 | 2020-05-15
6 | 2020-05-16 | Team meeting |  |  |  | 2
18 May 2020---24 May 2020 |  |  |  |  | Total | 15
1 | 2020-05-18 | Fix the defects of the integration test, Advisor meeting | Depend on the results of the integration test, I fix defects. The most common mistake is the spelling of upper and lower case. The most serious problem is the date input. The auction date cannot be displayed. Add a commodity function and make an appointment function cannot input date information, resulting in system errors. The result of the research is that the date input of HTML 5 could not support safari. The solution is to import a new date product. The download address is：https://www.layui.com/laydate/?alone |  |  | 9 | 基于集成测试的测试结果修复发现的缺陷。 主要内容是大小写错误，拍卖日期不能显示，新增商品功能和订单预约功能无法选择日期，导致系统报错。。 调查的结果是HTML5的日期输入存在浏览器支持的问题，在safair不能正常显示。 解决方法，导入新的日期产品，下载地址是：
2 | 2020-05-19
3 | 2020-05-20 | Fix the defects of the system test | Fix the defects of the system test. Optimize page-turning query function |  |  | 8
4 | 2020-05-21 | prepare the testing environment | Help our client to build a testing environment. |  |  | 8
5 | 2020-05-22
6 | 2020-05-23 | Team meeting |  |  |  | 2
25 May 2020---31 May 2020 |  |  |  |  | Total | 27
1 | 2020-05-25 | Fix the defects of the user acceptance test, Advisor meeting | Teach the client how to test the system. When they have questions, we will explain immediately or fix the defects. |  |  | 9
2 | 2020-05-26 | Write the installation manual | Write the install manual. 1. the installation JDK manual 2.the installation MySQL database manual 3.the installation Tomcat manual Provide verification method after installation prepare database initialization scripts. |  |  | 8
3 | 2020-05-27 | Prepare resources for Go-live and check the Go-live environment | 1.Package all required resources 2. Simulate the installation and deployment in the test environment. 3.Verify whether the go-live environment is available, including product version |  |  | 8
4 | 2020-05-28 | Support go-live | Support go-live Teach them how to use it Explain the problems often encountered |  |  | 8
5 | 2020-05-29 | Prepare the Project Closure document, client meeting | Evaluate our project management. 1.scope management. 2.schedule management. 3.quality management. 4.Communication management 5.risk Management. 6.Human resource management. summarize the experience of this project. |  |  | 9
6 | 2020-05-30 | Team meeting |  |  |  | 2
1 June 2020---7 June 2020 |  |  |  |  | Total | 44
1 | 2020-06-01
2 | 2020-06-02
3 | 2020-06-03 | Prepare Individual report | Summarize personal experience |  |  | 8
4 | 2020-06-04 | Review all documents. | Review the all of documents, Check all of the digital files Upload all materials to the cloud. |  |  | 8
5 | 2020-06-05
6 | 2020-06-06 | Team meeting |  |  |  | 2
8 June 2020---14 June 2020 |  |  |  |  | Total | 18
1 | 2020-06-08 | Prepare the panel interview.

## 2March
Weekly Timesheet
Week of: 2 March
Name: Cong Shang |  | Title: | Charity Online Store
DAY | Task | Start Time | End Time | Total Work Hours
Monday | Using brainstorming analyze all of projects and try to find a suitable project. | 9:30 | 23:00 | 8
Tuesday | Client Meeting | 9:30 | 23:00 | 1
Wednesday | contact with our client and try to find a project opportunity | 9:30 | 23:00 | 8
Thursday | get the first version of the requirement from the client. | 9:30 | 23:00 | 8
Friday | 0 | 9:30 | 23:00 | 0
Saturday | Team meeting | 9:30 | 23:00 | 2
WEEKLY TOTALS |  |  |  | 27

## 9 March
Weekly Timesheet
Week of: 9 March
Name: Cong Shang |  | Title: | Charity Online Store
DAY | Task | Start Time | End Time | Total Work Hours
Monday | Estimate the workload. | 9:30 | 23:00 | 4
Tuesday | Make the schedule plan and client meeting | 9:30 | 23:00 | 9
Wednesday | Make the schedule plan and prepare the scope statement document. | 9:30 | 23:00 | 8
Thursday | Write the project scope statement and refine the project schedule plan into work packages. | 9:30 | 23:00 | 8
Friday | Refine the work package of the project and sort the tasks. | 9:30 | 23:00 | 8
Saturday | Team meeting | 9:30 | 23:00 | 2
WEEKLY TOTALS |  |  |  | 39

## 16 March
Weekly Timesheet
Week of: 16 March
Name: Cong Shang |  | Title: | Charity Online Store
DAY | Task | Start Time | End Time | Total Work Hours
Monday | Update the schedule plan and identify stakeholders of this project.,Advisor meeting | 9:30 | 23:00 | 9
Tuesday | Prepare Personal CV and write the communication plan. Client meeting | 9:30 | 23:00 | 9
Wednesday | Prepare the proposal document. Focus on the methodologies of development and technical product. | 9:30 | 23:00 | 8
Thursday | Feasibility analysis，analysis of resources requirements and prepare client acceptance agreement | 9:30 | 23:00 | 8
Friday | 0 | 9:30 | 23:00 | 0
Saturday | Team meeting | 9:30 | 23:00 | 2
WEEKLY TOTALS |  |  |  | 36

## 23 March
Weekly Timesheet
Week of: 23 March
Name: Cong Shang |  | Title: | Charity Online Store
DAY | Task | Start Time | End Time | Total Work Hours
Monday | ,Advisor meeting | 9:30 | 23:00 | 1
Tuesday | Draw the use case diagram. | 9:30 | 23:00 | 8
Wednesday | Draw the system frameworks diagram and business flow- process diagram | 9:30 | 23:00 | 8
Thursday | Draw business flow- process diagram | 9:30 | 23:00 | 4
Friday | 0 | 9:30 | 23:00 | 0
Saturday | Team meeting | 9:30 | 23:00 | 2
WEEKLY TOTALS |  |  |  | 23

## 30 March
Weekly Timesheet
Week of: 30 March
Name: Cong Shang |  | Title: | Charity Online Store
DAY | Task | Start Time | End Time | Total Work Hours
Monday | 0 | 9:30 | 23:00 | 0
Tuesday | Review the system design, client meeting | 9:30 | 23:00 | 5
Wednesday | Prepare the development environment. | 9:30 | 23:00 | 8
Thursday | Build development envrioment. | 9:30 | 23:00 | 8
Friday | set up technical frameworks of the project. | 9:30 | 23:00 | 8
Saturday | Team meeting | 9:30 | 23:00 | 2
WEEKLY TOTALS |  |  |  | 31

## 06 April
Weekly Timesheet
Week of: 06 April
Name: Cong Shang |  | Title: | Charity Online Store
DAY | Task | Start Time | End Time | Total Work Hours
Monday | Verify that this framework is usable | 9:30 | 23:00 | 8
Tuesday | Develop the main page of this system and client meeting | 9:30 | 23:00 | 9
Wednesday | Show Goods on the main page. | 9:30 | 23:00 | 8
Thursday | Goods display by category. | 9:30 | 23:00 | 8
Friday | display the detailed information about the goods | 9:30 | 23:00 | 8
Saturday | Team meeting | 9:30 | 23:00 | 2
WEEKLY TOTALS |  |  |  | 43

## 13 April
Weekly Timesheet
Week of: 13 April
Name: Cong Shang |  | Title: | Charity Online Store
DAY | Task | Start Time | End Time | Total Work Hours
Monday | develop the auction function. | 9:30 | 23:00 | 8
Tuesday | develop the user login and logout function | 9:30 | 23:00 | 8
Wednesday | develop the auction function. | 9:30 | 23:00 | 8
Thursday | Develop the user register and password recover function | 9:30 | 23:00 | 8
Friday | check or update profile. | 9:30 | 23:00 | 8
Saturday | Team meeting | 9:30 | 23:00 | 2
WEEKLY TOTALS |  |  |  | 42

## 20 April
Weekly Timesheet
Week of: 20 April
Name: Cong Shang |  | Title: | Charity Online Store
DAY | Task | Start Time | End Time | Total Work Hours
Monday | develop viewing the display orders and make an appointment to pick up functions, Advisor meeting | 9:30 | 23:00 | 9
Tuesday | develop the cart function | 9:30 | 23:00 | 8
Wednesday | develop cart management function, client meeting | 9:30 | 23:00 | 9
Thursday | develop commodity management model. | 9:30 | 23:00 | 8
Friday | develop adding a new commodity | 9:30 | 23:00 | 8
Saturday | Team meeting | 9:30 | 23:00 | 2
WEEKLY TOTALS |  |  |  | 44

## 27 April
Weekly Timesheet
Week of: 27 April
Name: Cong Shang |  | Title: | Charity Online Store
DAY | Task | Start Time | End Time | Total Work Hours
Monday | develop the commodity management model, Advisor meeting | 9:30 | 23:00 | 9
Tuesday | develop the user management model | 9:30 | 23:00 | 8
Wednesday | Develop the user management model | 9:30 | 23:00 | 8
Thursday | Develop the order management model | 9:30 | 23:00 | 8
Friday | Develop the order management model | 9:30 | 23:00 | 8
Saturday | Team meeting | 9:30 | 23:00 | 2
WEEKLY TOTALS |  |  |  | 43

## 04 May
Weekly Timesheet
Week of: 04 May
Name: Cong Shang |  | Title: | Charity Online Store
DAY | Task | Start Time | End Time | Total Work Hours
Monday | Page beautification, Advisor meeting | 9:30 | 23:00 | 9
Tuesday | Page beautification | 9:30 | 23:00 | 8
Wednesday | Page beautification | 9:30 | 23:00 | 8
Thursday | Add about us page and contact us page | 9:30 | 23:00 | 8
Friday | 0 | 9:30 | 23:00 | 0
Saturday | Team meeting | 9:30 | 23:00 | 2
WEEKLY TOTALS |  |  |  | 35

## 11 May
Weekly Timesheet
Week of: 11 May
Name: Cong Shang |  | Title: | Charity Online Store
DAY | Task | Start Time | End Time | Total Work Hours
Monday | Advisor meeting | 9:30 | 23:00 | 1
Tuesday | 0 | 9:30 | 23:00 | 0
Wednesday | Code review | 9:30 | 23:00 | 4
Thursday | prepare the testing environment. | 9:30 | 23:00 | 8
Friday | 0 | 9:30 | 23:00 | 0
Saturday | Team meeting | 9:30 | 23:00 | 2
WEEKLY TOTALS |  |  |  | 15

## 18 May
Weekly Timesheet
Week of: 18 May
Name: Cong Shang |  | Title: | Charity Online Store
DAY | Task | Start Time | End Time | Total Work Hours
Monday | Fix the defects of the integration test, Advisor meeting | 9:30 | 23:00 | 9
Tuesday | 0 | 9:30 | 23:00 | 0
Wednesday | Fix the defects of the system test | 9:30 | 23:00 | 8
Thursday | prepare the testing environment | 9:30 | 23:00 | 8
Friday | 0 | 9:30 | 23:00 | 0
Saturday | Team meeting | 9:30 | 23:00 | 2
WEEKLY TOTALS |  |  |  | 27

## 25 May
Weekly Timesheet
Week of: 25 May
Name: Cong Shang |  | Title: | Charity Online Store
DAY | Task | Start Time | End Time | Total Work Hours
Monday | Fix the defects of the user acceptance test, Advisor meeting | 9:30 | 23:00 | 9
Tuesday | Write the installation manual | 9:30 | 23:00 | 8
Wednesday | Prepare resources for Go-live and check the Go-live environment | 9:30 | 23:00 | 8
Thursday | Support go-live | 9:30 | 23:00 | 8
Friday | Prepare the Project Closure document, client meeting | 9:30 | 23:00 | 9
Saturday | Team meeting | 9:30 | 23:00 | 2
WEEKLY TOTALS |  |  |  | 44

## 1 June
Weekly Timesheet
Week of: 01 June
Name: Cong Shang |  | Title: | Charity Online Store
DAY | Task | Start Time | End Time | Total Work Hours
Monday | 0 | 9:30 | 23:00 | 0
Tuesday | 0 | 9:30 | 23:00 | 0
Wednesday | Prepare Individual report | 9:30 | 23:00 | 8
Thursday | Review all documents. | 9:30 | 23:00 | 8
Friday | 0 | 9:30 | 23:00 | 0
Saturday | Team meeting | 9:30 | 23:00 | 2
WEEKLY TOTALS |  |  |  | 18