## Project diary
Individual Log
Name : Michael (Guozhi Yin) |  |  | Project name: Charity Second-hand Online Store
Date | Time | Event | Details
2020-03-02 | 9:30am~11:30pm | Brainstorming Build team | Discuss which project to do with teammates. We decided to develop a website to help people archive email. Analyse main functions of the product and the strength and weakness of teammates. Find another teammate to join us. So, our team has three members.
2020-03-03 | 9:30am~11:30pm | Meeting with the client System analysis | Supervisor Robert refused us to do the project of archive email, so we chose another project called salvation army second-hand online stroe. Analysing main functions and the strength and weakness of teammates. Meeting with the client to discuss the project purpose.
2020-03-04 | 9:30am~11:30pm | Project plan | Disscuss how to implement the project. We decided to use scrum methodology, and take 5 milestones to finish it. We also discussed teammates' responsibility.
2020-03-05 | 9:30am~11:30pm | Bid document | I Prepared the bid document.
2020-03-06 | 9:30am~11:30pm | Prepare Bid document | Prepare Bid document and get the approval from Robert
2020-03-07 | 9:30am~11:30pm | Team meeting Do research | I brainstormed with teammates the main requirement, and did some research on the Trade me . The team decided to have a face-to-face meeting with the client next week.
2020-03-09 | 9:30am~11:30pm | Product plan Brainstorm product functions Make initial prototype | Analysing the project plan. Disscuss the main product functions and made a simple prototype for tomorrow's client meeting.
2020-03-10 | 9:30am~11:30pm | Meeting with the client Do research Make prototype | Disscuss requirements with the client. The client suggested to make it auction mode because she cannot upload all things on the website. Do research in the store. The store is running the auction activity. Design the new prototype.
2020-03-11 | 9:30am~11:30pm | Make prototype | Design and make the new prototype.
2020-03-12 | 9:30am~11:30pm | Discuss requirement Make prototype | Discuss requirements with teammates. Make prototype .
2020-03-14 | 9:30am~11:30pm | Team meeting Documentation | Talking with teammates how to translate requirement to product function. Prepare meeting agenda and meeting minutes.
2020-03-16 | 9:30am~11:30pm | Project meeting with advisor Brainstorming system analysis and design | Project meeting with advisor. Introduced our project and teammates. Discussed how to write the system analysis and design document.
2020-03-17 | 9:30am~11:30pm | Client meeting Prepare CV | Discussed requireements with the client. Prepared CV for the proposal.
2020-03-18 | 9:30am~11:30pm | Proposal document Team agreement | prepare proposal document. Prepare the team agreement.
2020-03-19 | 9:30am~11:30pm | Project meeting with Robert Modify proposal | Project meeting with Robert. We need to modify proposal document. He said that this project was not coordinated with the whole Salvation Army church. We should do more research for the project. A teammate left our team because of the teamwork problem, so the team was under pressure.
2020-03-20 | 9:30am~11:30pm | Modify proposal | Modify proposal document. To modify the purpose of the project and other detailed information.
2020-03-21 | 9:30am~11:30pm | Team meeting Documentation | Discuss how to solve the personnel risk. Because the left teammate is project, and she was responsible for the front-end development. I could not find another teammate to solve the problem. I would take on the position of project manager, and Cong Shang would be responsible for the front-end development.
2020-03-23 | 9:30am~11:30pm | Project meeting with advisor Modify prototype Requirement analysis | Project meeting with advisor. Advisor suggested that we could keep going to the phase of planning. Although this project is not coordinated with the whold Salvation Army church, it can be used for all charity second-hand stores. We need to modify the purpose of the project, to change the previous purpose. Prepare requirement analysis document.
2020-03-24 | 9:30am~11:30pm | Requirement analysis | Prepare requirement analysis document.
2020-03-25 | 9:30am~11:30pm | Requirement analysis | Modify requirement analysis document.
2020-03-26 | 9:30am~11:30pm | Database design | Design database table structure.
2020-03-27 | 9:30am~11:30pm | Database design | Design database table structure.
2020-03-28 | 9:30am~11:30pm | Team meeting Documentation | Project meeting with teammate about how to modify project schedule so that the delivery time can be guaranteed. Discuss database design and draw ER diagram. Prepare meeting agenda and meeting minutes.
2020-03-30 | 9:30am~11:30pm | Do research | Do research for the system analysis and design.
2020-03-31 | 9:30am~11:30pm | Client meeting System analysis and design | Discussed product function with the client and let her know a teammate left our team. So, we re-planed the project scope and deleting the donation function. Prepare system analysis and design document.
2020-04-01 | 9:30am~11:30pm | Requirement analysis System analysis and design | Prepare system analysis and design document. Modify requirement analysis document according to the new project scope.
2020-04-02 | 9:30am~11:30pm | System analysis and design | Prepare system analysis and design document.
2020-04-03 | 9:30am~11:30pm | Test plan | Prepare test plan document
2020-04-04 | 9:30am~11:30pm | Team meeting Documentation | Discuss how to modify the new project schedule and confirmed the new schedule. Prepare meeting agenda and meeting minutes.
2020-04-06 | 9:30am~11:30pm | Test case | Do research about how to write test case. Prepare test case document.
2020-04-07 | 9:30am~11:30pm | Client meeting Test plan Test case | Confirmed the final functions with the client. Do research for writing test plan and modify test plan. Prepare test case document.
2020-04-08 | 9:30am~11:30pm | Test plan Test case | Modify test plan. Prepare test case document.
2020-04-09 | 9:30am~11:30pm | Test plan Test case | Modify test plan. Prepare test case document.
2020-04-10 | 9:30am~11:30pm | Test plan Test case | Modify test plan. Prepare test case document.
2020-04-11 | 9:30am~11:30pm | Team meeting Documentation | Disscuss development plan. Prepare meeting agenda and meeting minutes.
2020-04-13 | 9:30am~11:30pm | Modify prototype | Modify prototype (add bid history and shopping cart)
2020-04-14 | 9:30am~11:30pm | Do research | Do research for system analysis and design
2020-04-15 | 9:30am~11:30pm | Modify prototype | Modify prototype (add bid history and shopping cart)
2020-04-16 | 9:30am~11:30pm | System analysis and design | Prepare system analysis and design
2020-04-17 | 9:30am~11:30pm | System analysis and design | Prepare system analysis and design
2020-04-18 | 9:30am~11:30pm | Team meeting Documentation | Disscuss how to adjust the layout of the mainpage. Prepare meeting agenda and meeting minutes.
2020-04-20 | 9:30am~11:30pm | Advisor meeting | Advisor meeting with Ian Report the progress with advisor and let him help us review proposal. Advisor Ian gave us a lot of suggestions for the proposal document.
2020-04-21 | 9:30am~11:30pm | Proposal document | Modify the final version of the proposal document Do methodology research and add references.
2020-04-22 | 9:30am~11:30pm | System analysis and design | Prepare the system analysis and design document
2020-04-23 | 9:30am~11:30pm | Proposal document System analysis and design | Prepare system analysis and design document. Modify the final version of the proposal document. Add SWOT at the end of the methodology.
2020-04-24 | 9:30am~11:30pm | System analysis and design | Prepare the system analysis and design document
2020-04-25 | 9:30am~11:30pm | Team meeting Documentation | Disscuss how to add map on the page of contact us. Prepare meeting agenda and meeting minutes.
2020-04-27 | 9:30am~11:30pm | Advisor meeting | Advisor meeting with Ian and modify two meeting minutes
2020-04-28 | 9:30am~11:30pm | System analysis and design | Modify the system analysis and design document
2020-04-29 | 9:30am~11:30pm | The function of about us | Search photos for the function of about us. I downloaded some pics to decorate the page.
2020-04-30 | 9:30am~11:30pm | Prepare the introduction for the function of about us | Do research to understand the charity background, and write the introduction for the function of about us.
2020-05-01 | 9:30am~11:30pm | Mid project presentation | Prepare mid project presentation document according to supervisor's demands. I prepare to write it in 6 parts: cover, project purpose, project risk, Gantt chart, the solutions to project risk and deliverable list.
2020-05-02 | 9:30am~11:30pm | Team meeting Documentation | Team meeting with teammate (Discuss development issue on goods management) Disscuss how to solve the problem of database timezone. Prepare meeting agenda and meeting minutes.
2020-05-04 | 9:30am~11:30pm | Advisor meeting | Advisor meeting with Ian to report the progress of the project.
2020-05-05 | 9:30am~11:30pm | Prototype Disscuss problem on goods management | Modify prototype (add user management) Discuss development on goods management. Administrator cannot delete items if the auction starts.
2020-05-06 | 9:30am~11:30pm | System analysis and design | Modify system analysis and design
2020-05-07 | 9:30am~11:30pm | Mid project presentation | Modify the powerpoint document (Add the previous Gantt chart to compare the current one)
2020-05-08 | 9:30am~11:30pm | Mid project presentation | Practise to show the presentation.
2020-05-09 | 9:30am~11:30pm | Team meeting Documentation | Project meeting with teammate (Discuss development issue on about us) Practise to show the presentation with teammate. Prepare meeting agenda and meeting minutes.
2020-05-11 | 9:30am~11:30pm | Advisor meeting Documentation | Advisor meeting with Ian Prepare milestone report for milestone1 (proposal phase) and milestone 2 (system design phase)
2020-05-12 | 9:30am~11:30pm | Mid project presentation | Show the presentation to supervisor Robert and answer his questions. 1.Q: What methodology did you use? A: Prototyping methodology. 2.Q: Why does your product use the auction function? A: Because the store is running the auction activity and it is the client’s requirement. The second-hand store is special. One stuff just one, so it is not suitable for the store to post everything online. 3.Q: What does your product bring to customers? A: It is easier for customers to buy something online and improve user shopping experience.
2020-05-13 | 9:30am~11:30pm | Test plan | Modify test plan. Update schedule list.
2020-05-14 | 9:30am~11:30pm | Prepare test environment | Prepare test environment Install Tomcat Test to run the software package successfully.
2020-05-15 | 9:30am~11:30pm | Integration testing | Integration testing and record bugs or defects in the test case document.
2020-05-16 | 9:30am~11:30pm | Team meeting Documentation | Project meeting with teammate (Discuss how to modify system testing case) Discuss how to fix the bugs from the integration testing. Prepare meeting agenda and meeting minutes.
2020-05-18 | 9:30am~11:30pm | Advisor meeting Documentation | Advisor meeting with Ian to report the progress of the project. Prepare milestone report for milestone3 (development phase)
2020-05-19 | 9:30am~11:30pm | Integration testing report System testing | Prepare integration testing report. The purpose and statistic chart should be included. Start the system testing
2020-05-20 | 9:30am~11:30pm | Integration testing report System testing report | Verify if the bugs have been fixed from the integration testing. Update the integration testing report. Prepare the system testing report.
2020-05-21 | 9:30am~11:30pm | Prepare user manual prepare training document System testing report | Prepare user manual prepare training document Verify if the bugs have been fixed from the system testing. Update the system testing report.
2020-05-22 | 9:30am~11:30pm | Client meeting Set up test environment for the client Client training | Project meeting with the client. Set up test environment for the client The team give the client a training to help her understand how to use the system and how to execute the user acceptance testing.
2020-05-23 | 9:30am~11:30pm | Team meeting Documentation | Project meeting with teammate (Discuss something about the client handover) Prepare meeting agenda and meeting minutes.
2020-05-25 | 9:30am~11:30pm | Advisor meeting Documentation | Advisor meeting with Ian to report the progress of the project and discuss the client handover. Prepare milestone report for milestone4 (testing phase)
2020-05-26 | 9:30am~11:30pm | Prepare project closure report | Prepare project closure report
2020-05-27 | 9:30am~11:30pm | Project closure report Client receipt and Client acceptance document | Prepare project closure report Prepare client receipt and client acceptance document
2020-05-28 | 9:30am~11:30pm | Prepare 1 page project handbook Modify project closure report | Prepare 1 page project handbook Modify project closure report
2020-05-29 | 9:30am~11:30pm | Go live Client handover | Go live and client handover The team has completed the client handover of all related documents and project code.
2020-05-30 | 9:30am~11:30pm | Team meeting Academic handover | Project meeting with teammate (Discuss the academic handover) Prepare the related documents for the academic handover
2020-05-31 | 9:30am~11:30pm | Academic handover | Prepare the related documents for the academic handover
2020-06-01 | 9:30am~11:30pm | Advisor meeting Documentation | Advisor meeting with Ian to report the progress of the project and discuss the academic handover. Prepare milestone report for milestone5 (client handover phase)
2020-06-02 | 9:30am~11:30pm | Academic handover | Prepare and update the related documents for the academic handover
2020-06-03 | 9:30am~11:30pm | Academic handover | Prepare and update the related documents for the academic handover
2020-06-04 | 9:30am~11:30pm | Academic handover | Prepare and update the related documents for the academic handover
2020-06-05 | 9:30am~11:30pm | Academic handover | Prepare and update the related documents for the academic handover
2020-06-06 | 9:30am~11:30pm | Team meeting Academic handover | Project meeting with teammate (review the academic handover) Prepare and update the related documents for the academic handover
2020-06-07 | 9:30am~11:30pm | Academic handover | Prepare and update the related documents for the academic handover