## 2~8 Mar
Weekly Timesheet
Week of: 2~8 March
Name: Guozhi Yin |  | Title: Charity Second-hand Online Store
DAY | Tasks | Start Time | End Time | Total Work Hours
Monday | Discuss which project to do with teammates. Find another member to join our team. Analyse main requirements and the strength and weakness of teammates. | 9:30 | 23:30 | 8
Tuesday | System analysis (include risk analysis, technical analysis and feasibility analysis) Meeting with the client and discuss the purpose of the project. | 9:30 | 23:30 | 8
Wednesday | Disscuss how to implement the project with teammates | 9:30 | 23:30 | 2
Thursday | Analyse the main requirements of the project. Prepare the first version of the requirement. | 9:30 | 23:30 | 8
Friday | Prepare Bid document | 9:30 | 23:30 | 8
Saturday | Team meeting Do research on auticon website. Documentation(meeting agenda and minutes, project diary, other reports) | 9:30 | 23:30 | 6
Sunday |  | 9:30 | 23:30
WEEKLY TOTALS |  |  |  | 40

## 9~15 Mar
Weekly Timesheet
Week of: 9~15 March
Name: Guozhi Yin |  | Title: Charity Second-hand Online Store
DAY | Tasks | Start Time | End Time | Total Work Hours
Monday | Project plan Brainstorm product functions and requirements Make prototype | 9:30 | 23:30 | 9
Tuesday | Client meeting Brainstorm product functions and requirements Make prototype | 9:30 | 23:30 | 8
Wednesday | Make prototype | 9:30 | 23:30 | 8
Thursday | Make prototype Discuss the requirements | 9:30 | 23:30 | 9
Friday |  | 9:30 | 23:30 | 0
Saturday | Team meeting Documentation(meeting agenda and minutes, project diary, other reports) | 9:30 | 23:30 | 5
Sunday |  | 9:30 | 23:30 | 0
WEEKLY TOTALS |  |  |  | 39

## 16~22 Mar
Weekly Timesheet
Week of: 16~22 March
Name: Guozhi Yin |  | Title: Charity Second-hand Online Store
DAY | Tasks | Start Time | End Time | Total Work Hours
Monday | Project meeting with advisor Analyse the requirements of proposal | 9:30 | 23:30 | 2
Tuesday | Meeting with the client Prepare personal CV for the proposal | 9:30 | 23:30 | 4
Wednesday | Prepare proposal Prepare the team agreement | 9:30 | 23:30 | 9
Thursday | Project meeting with Robert Modify proposal | 9:30 | 23:30 | 8
Friday | Modify proposal | 9:30 | 23:30 | 8
Saturday | Team meeting Documentation(meeting agenda and minutes, project diary, other reports) | 9:30 | 23:30 | 5
Sunday |  | 9:30 | 23:30 | 0
WEEKLY TOTALS |  |  |  | 36

## 23~29 Mar
Weekly Timesheet
Week of: 23~29 March
Name: Guozhi Yin |  | Title: Charity Second-hand Online Store
DAY | Tasks | Start Time | End Time | Total Work Hours
Monday | Project meeting with Ian. Modify proposal Prepare requirement analysis document | 9:30 | 23:30 | 8
Tuesday | Prepare requirement analysis document | 9:30 | 23:30 | 8
Wednesday | Modify requirement analysis document | 9:30 | 23:30 | 4
Thursday | Database design | 9:30 | 23:30 | 8
Friday | Database design | 9:30 | 23:30 | 8
Saturday | Team meeting Documentation(meeting agenda and minutes, project diary, other reports) | 9:30 | 23:30 | 7
Sunday |  | 9:30 | 23:30
WEEKLY TOTALS |  |  |  | 43

## 30~5 Apr
Weekly Timesheet
Week of: 30 Mar~05 Apr
Name: Guozhi Yin |  | Title: Charity Second-hand Online Store
DAY | Tasks | Start Time | End Time | Total Work Hours
Monday | Do research for system analysis and design | 9:30 | 23:30 | 6
Tuesday | Client meeting Prepare system analysis and design | 9:30 | 23:30 | 6
Wednesday | Prepare system analysis and design Modify requirement analysis document | 9:30 | 23:30 | 8
Thursday | Prepare system analysis and design | 9:30 | 23:30 | 5
Friday | Prepare test plan | 9:30 | 23:30 | 8
Saturday | Team meeting Documentation(meeting agenda and minutes, project diary, other reports) | 9:30 | 23:30 | 7
Sunday |  | 9:30 | 23:30 | 0
WEEKLY TOTALS |  |  |  | 40

## 6~12 Apr
Weekly Timesheet
Week of: 06~12 Apr
Name: Guozhi Yin |  | Title: Charity Second-hand Online Store
DAY | Tasks | Start Time | End Time | Total Work Hours
Monday | Prepare test case | 9:30 | 23:30 | 8
Tuesday | Client meeting Modify test plan Prepare test case | 9:30 | 23:30 | 7
Wednesday | Modify test plan Prepare test case | 9:30 | 23:30 | 6
Thursday | Modify test plan Prepare test case | 9:30 | 23:30 | 8
Friday | Modify test plan Prepare test case | 9:30 | 23:30 | 5
Saturday | Team meeting Documentation(meeting agenda and minutes, project diary, other reports) | 9:30 | 23:30 | 6
Sunday |  | 9:30 | 23:30 | 0
WEEKLY TOTALS |  |  |  | 40

## 13~19 Apr
Weekly Timesheet
Week of: 13~19 Apr
Name: Guozhi Yin |  | Title: Charity Second-hand Online Store
DAY | Tasks | Start Time | End Time | Total Work Hours
Monday | Modify prototype | 9:30 | 23:30 | 2
Tuesday | Do research for system analysis and design | 9:30 | 23:30 | 2
Wednesday | Modify prototype | 9:30 | 23:30 | 4
Thursday | Prepare system analysis and design document | 9:30 | 23:30 | 2
Friday | Prepare system analysis and design document | 9:30 | 23:30 | 2
Saturday | Team meeting Documentation(meeting agenda and minutes, project diary, other reports) | 9:30 | 23:30 | 6
Sunday |  | 9:30 | 23:30 | 0
WEEKLY TOTALS |  |  |  | 18

## 20~26 Apr
Weekly Timesheet
Week of: 20~26 Apr
Name: Guozhi Yin |  | Title: Charity Second-hand Online Store
DAY | Tasks | Start Time | End Time | Total Work Hours
Monday | Advisor meeting Prepare system analysis and design document | 9:30 | 23:30 | 2
Tuesday | Modify the final version of the proposal document | 9:30 | 23:30 | 2
Wednesday | Prepare system analysis and design document | 9:30 | 23:30 | 2
Thursday | Prepare system analysis and design document Modify the final version of the proposal document | 9:30 | 23:30 | 2
Friday | Prepare system analysis and design document | 9:30 | 23:30 | 3
Saturday | Team meeting Documentation(meeting agenda and minutes, project diary, other reports) | 9:30 | 23:30 | 6
Sunday |  | 9:30 | 23:30 | 0
WEEKLY TOTALS |  |  |  | 17

## 27 Apr~03 May
Weekly Timesheet
Week of: 27 Apr~03 May
Name: Guozhi Yin |  | Title: Charity Second-hand Online Store
DAY | Tasks | Start Time | End Time | Total Work Hours
Monday | Advisor meeting Prepare mid project presentation document | 9:30 | 23:30 | 2
Tuesday | Modify system analysis and design document | 9:30 | 23:30 | 2
Wednesday | Search photos for the function of about us | 9:30 | 23:30 | 2
Thursday | Prepare the content for the function of about us | 9:30 | 23:30 | 2
Friday | Prepare mid project presentation document | 9:30 | 23:30 | 5
Saturday | Team meeting Documentation(meeting agenda and minutes, project diary, other reports) | 9:30 | 23:30 | 5
Sunday |  | 9:30 | 23:30 | 0
WEEKLY TOTALS |  |  |  | 18

## 04~10 May
Weekly Timesheet
Week of: 04~10 May
Name: Guozhi Yin |  | Title: Charity Second-hand Online Store
DAY | Tasks | Start Time | End Time | Total Work Hours
Monday | Project meeting with advisor Prepare mid project presentation | 9:30 | 23:30 | 2
Tuesday | Modify prototype (add user management) Discuss development on goods management | 9:30 | 23:30 | 2
Wednesday | Modify system analysis and design document | 9:30 | 23:30 | 2
Thursday | Prepare mid project presentation | 9:30 | 23:30 | 2
Friday | Prepare mid project presentation | 9:30 | 23:30 | 4
Saturday | Team meeting Documentation(meeting agenda and minutes, project diary, other reports) | 9:30 | 23:30 | 7
Sunday |  | 9:30 | 23:30 | 0
WEEKLY TOTALS |  |  |  | 19

## 11~17 May
Weekly Timesheet
Week of: 11~17 May
Name: Guozhi Yin |  | Title: Charity Second-hand Online Store
DAY | Tasks | Start Time | End Time | Total Work Hours
Monday | Project meeting with advisor Prepare mid project presentation | 9:30 | 23:30 | 2
Tuesday | Mid-project presentation | 9:30 | 23:30 | 1
Wednesday | Modify testing plan | 9:30 | 23:30 | 1
Thursday | Prepare test environment | 9:30 | 23:30 | 6
Friday | Integration testing | 9:30 | 23:30 | 6
Saturday | Team meeting Documentation(meeting agenda and minutes, project diary, other reports) Prepare milestone 1,2 report | 9:30 | 23:30 | 8
Sunday |  | 9:30 | 23:30 | 0
WEEKLY TOTALS |  |  |  | 24

## 18~24 May
Weekly Timesheet
Week of: 18~24 May
Name: Guozhi Yin |  | Title: Charity Second-hand Online Store
DAY | Tasks | Start Time | End Time | Total Work Hours
Monday | Project meeting with advisor Prepare milestone report for milestone 3(Development phase) | 9:30 | 23:30 | 4
Tuesday | Prepare integration testing report System testing | 9:30 | 23:30 | 8
Wednesday | Prepare integration testing report System testing | 9:30 | 23:30 | 7
Thursday | Prepare user manual prepare training document | 9:30 | 23:30 | 7
Friday | Project meeting with the client Set up test environment for the client Client training | 9:30 | 23:30 | 2
Saturday | Team meeting Documentation(meeting agenda and minutes, project diary, other reports) | 9:30 | 23:30 | 7
Sunday |  | 9:30 | 23:30 | 0
WEEKLY TOTALS |  |  |  | 35

## 25~31 May
Weekly Timesheet
Week of: 25~31 May
Name: Guozhi Yin |  | Title: Charity Second-hand Online Store
DAY | Tasks | Start Time | End Time | Total Work Hours
Monday | Project meeting with advisor Prepare milestone report for milestone 4(Testing phase) | 9:30 | 23:30 | 4
Tuesday | Prepare project closure report | 9:30 | 23:30 | 5
Wednesday | Prepare project closure report Prepare client receipt and client acceptance document | 9:30 | 23:30 | 7
Thursday | Prepare 1 page project handbook Modify project closure report | 9:30 | 23:30 | 6
Friday | Project meeting with the client System go-live | 9:30 | 23:30 | 1
Saturday | Prepare academic handover | 9:30 | 23:30 | 7
Sunday | Prepare academic handover | 9:30 | 23:30 | 8
WEEKLY TOTALS |  |  |  | 38

## 1~7 June
Weekly Timesheet
Week of: 1~7 June
Name: Guozhi Yin |  | Title: Charity Second-hand Online Store
DAY | Tasks | Start Time | End Time | Total Work Hours
Monday | Project meeting with advisor Prepare milestone report for milestone 5(Client handover phase) | 9:30 | 23:30 | 4
Tuesday | Prepare academic handover | 9:30 | 23:30 | 7
Wednesday | Prepare academic handover | 9:30 | 23:30 | 7
Thursday | Prepare academic handover | 9:30 | 23:30 | 7
Friday | Prepare academic handover | 9:30 | 23:30 | 7
Saturday | Prepare academic handover | 9:30 | 23:30 | 7
Sunday | Prepare academic handover | 9:30 | 23:30 | 6
WEEKLY TOTALS |  |  |  | 45