## Project diary
Project Diary
Team members : Michael (Guozhi Yin) , Cong Shang |  |  | Project name: Charity Second-hand Online Store
Date | Time | Event | Details | Log by
2020-03-02 | 9:30am~11:30pm | Brainstorming Build team | Discuss which project to do with teammates. The only project which can be considered price snitch. After contacting with the client, their demand is to develop a mobile application. We don't have the mobile APP and web crawler development experience, so the technical risk is very high. Finally, we have to abandon this project. We decided to develop a website to help people archive email. Analyse main functions of the product and the strength and weakness of teammates. Find another teammate to join us. So, our team has three members. | Michael
2020-03-03 | 9:30am~11:30pm | Meeting with the client System analysis | Supervisor Robert refused us to do the project of archive email, so we chose another project called salvation army second-hand online stroe. Analysing main functions and the strength and weakness of teammates. Meeting with the client to discuss the project purpose. | Michael
2020-03-04 | 9:30am~11:30pm | Project plan | Disscuss how to implement the project. We advised our client to build a online store to sell all goods. Client suggested that it was impossible because every item was unique. They do not have energy to upload everything to the online store. After discussion, the client decided to build an auction system. We decided to use scrum methodology, and take 5 milestones to finish it. We also discussed teammates' responsibility. | Michael
2020-03-05 | 9:30am~11:30pm | Bid document | Prepared the bid document. | Michael
2020-03-06 | 9:30am~11:30pm | Prepare Bid document | Prepare Bid document and get the approval from Robert We pointed out this system should have two types of user, normal user and administrator, and should divide to online store site and management site. | Michael
2020-03-07 | 9:30am~11:30pm | Team meeting Do research | brainstorming with teammates the main requirement, and did some research on the Trade me . The team decided to have a face-to-face meeting with the client next week.
2020-03-09 | 9:30am~11:30pm | Product plan Brainstorm product functions Make initial prototype Estimate the workload. | Analysing the project plan. Disscuss the main product functions and made a simple prototype for tomorrow's client meeting. Beas on the requirements, Cong estimated the workload. Because of a lot of unsure things in this step, Cong only estimated it by his experience. | Michael
2020-03-10 | 9:30am~11:30pm | Meeting with the client Do research Make prototype Make schedule plan | Disscuss requirements with the client. The client suggested to make it auction mode because she cannot upload all things on the website. Do research in the store. The store is running the auction activity. Design the new prototype. Using Microsoft Project to design the project schedule plan. Firstly, team identified all the milestones， because the time of the project is fixed. Secondly, allocated the first level of work based on the results of the estimated workload. | Michael
2020-03-11 | 9:30am~11:30pm | Make prototype Make the schedule plan prepare the scope statement document. | Designed and made the new prototype. Designed the project schedule plan. Defined the scope of the project. | Michael
2020-03-12 | 9:30am~11:30pm | Discuss requirement Make prototype Write the project scope statement and refine the project schedule plan into work packages | Discussed requirements with teammates. Made prototype . Finished the scope statement document. Prepared the work breakdown structure (WBS) of this project. Refined the project schedule plan into work packages. | Michael
2020-03-13 | 9:30am~11:30pm | Refine the work package of the project and sort the tasks. | Refine the work package of the project and sort the tasks. | Michael
2020-03-14 | 9:30am~11:30pm | Team meeting Documentation | Talking with teammates how to translate requirement to product function. Prepare meeting agenda and meeting minutes. | Michael
2020-03-16 | 9:30am~11:30pm | Project meeting with advisor Brainstorming system analysis and design Update the schedule plan and identify stakeholders of this project | Project meeting with advisor. Introduced our project and teammates. Discussed how to write the system analysis and design document. Identified project stakeholders and record them in the stakeholder register | Michael
2020-03-17 | 9:30am~11:30pm | Client meeting Prepare CV | Discussed requireements with the client. Prepared CV for the proposal. | Michael
2020-03-18 | 9:30am~11:30pm | Proposal document Team agreement | prepare proposal document. Prepare the team agreement. Did research on methodologies of development. Compared the main of the methodologies. Such as Waterfall, rapid application, agile, prototyping. Compared the popular databases, and chose one of them for this project. Team chose MySQL because it was free and easy to use. | Michael
2020-03-19 | 9:30am~11:30pm | Project meeting with Robert Modify proposal | Project meeting with Robert. We need to modify proposal document. He said that this project was not coordinated with the whole Salvation Army church. We should do more research for the project. A teammate left our team because of the teamwork problem, so the team was under pressure. Feasibility analysis of the project in aspects of finance, time, technology and market Analysis of resources requirements for the project Prepare client acceptance agreement | Michael
2020-03-20 | 9:30am~11:30pm | Modify proposal | Modify proposal document. To modify the purpose of the project and other detailed information. | Michael
2020-03-21 | 9:30am~11:30pm | Team meeting Documentation | Discuss how to solve the personnel risk. Because the left teammate is project, and she was responsible for the front-end development. I could not find another teammate to solve the problem. I would take on the position of project manager, and Cong Shang would be responsible for the front-end development. | Michael
2020-03-23 | 9:30am~11:30pm | Project meeting with advisor Modify prototype Requirement analysis | Project meeting with advisor. Advisor suggested that we could keep going to the phase of planning. Although this project is not coordinated with the whold Salvation Army church, it can be used for all charity second-hand stores. We need to modify the purpose of the project, to change the previous purpose. Prepare requirement analysis document. | Michael
2020-03-24 | 9:30am~11:30pm | Requirement analysis Draw the use case diagram | Prepare requirement analysis document. Design use case diagram according to user requirements | Michael
2020-03-25 | 9:30am~11:30pm | Requirement analysis Draw the system frameworks diagram and business flow process diagram | Modify requirement analysis document. System structure design. Draw a system structure diagram. Draw business flow process diagram depends on user's requirements. | Michael
2020-03-26 | 9:30am~11:30pm | Database design Draw business flow process diagram | Design database table structure. A total of 12 business flow diagram were drawn. | Michael
2020-03-27 | 9:30am~11:30pm | Database design | Design database table structure. | Michael
2020-03-28 | 9:30am~11:30pm | Team meeting Documentation | Project meeting with teammate about how to modify project schedule so that the delivery time can be guaranteed. Discuss database design and draw ER diagram. Prepare meeting agenda and meeting minutes. | Michael
2020-03-30 | 9:30am~11:30pm | Do research | Do research for the system analysis and design. | Michael
2020-03-31 | 9:30am~11:30pm | Client meeting System analysis and design | Discussed product function with the client and let her know a teammate left our team. So, we re-planed the project scope and deleting the donation function. Prepare system analysis and design document. | Michael
2020-04-01 | 9:30am~11:30pm | Requirement analysis System analysis and design Prepare the development environment. | Prepare system analysis and design document. Modify requirement analysis document according to the new project scope. Prepare development envrioment. Installation of development tools, including JDK ，Eclipse, MySQL. | Michael
2020-04-02 | 9:30am~11:30pm | System analysis and design Build development envrioment. | Prepare system analysis and design document. Prepare development envrioment. | Michael
2020-04-03 | 9:30am~11:30pm | Test plan Set up technical frameworks of the project. | Prepare test plan document Analyse the more popular technical frameworks such as Struts, JSP，Spring MVC, Hibernate, MyBatis and so on. Finally, team decided to use basic technology. JSP +Servlet. | Michael
2020-04-04 | 9:30am~11:30pm | Team meeting Documentation | Discuss how to modify the new project schedule and confirmed the new schedule. Prepare meeting agenda and meeting minutes. | Michael
2020-04-06 | 9:30am~11:30pm | Test case Verify that this framework is usable | Do research about how to write test case. Prepare test case document. Using the JDBC test the database connection. Try to write a demo code to prove that this framework is usable | Michael
2020-04-07 | 9:30am~11:30pm | Client meeting Test plan Test case Develop the main page of this system | Confirmed the final functions with the client. Do research for writing test plan and modify test plan. Prepare test case document. Import the front page template into my project. Adjust the layout of the page according to the prototype. Separate the top and bottom of the page into a separate JSP file. | Michael
2020-04-08 | 9:30am~11:30pm | Test plan Test case Develop the main page. | Modify test plan. Prepare test case document. There is no commodity data in the database, Cong inserted some fake commodities data into the database for testing. According to the requirement document, the main page will display 12 goods nearest to the closing time. The problem on this page is that the size of a commodity picture affects the layout of the page. The solution is that I use CSS to picture showing in the fixed size. | Michael
2020-04-09 | 9:30am~11:30pm | Test plan Test case Goods display by category. | Modify test plan. Prepare test case document. In this project, the main page has five different categories. | Michael
2020-04-10 | 9:30am~11:30pm | Test plan Test case Display the detailed information about the goods | Modify test plan. Prepare test case document. Using one-page display the commodity information. The challenge of this function is the countdown tool. Cong used javascript to judge how long will the commodity close. | Michael
2020-04-11 | 9:30am~11:30pm | Team meeting Documentation | Disscuss development plan. Prepare meeting agenda and meeting minutes. | Michael
2020-04-13 | 9:30am~11:30pm | Modify prototype Develop the auction function. | Modify prototype (add bid history and shopping cart) The function of commodity auction is the core of an auction website. It's also a very challenging job. The biggest problem is that the system does not know when to end the auction. After thinking, there are two solutions: 1. when the system starts, the system loads all product information into the memory. Use the close time of commodities in memory and the system time to match continuously, if the match reaches the close time, the commodity will stop the auction and generates an order. The advantage of this scheme is that it can control the close time of the auction very accurately. The disadvantages are: the development is very difficult and the workload is large. The first step is to load all commodities information into memory during the system startup phase, and start a separate thread for monitoring the time. Another difficulty is to ensure that the data in memory must be consistent with the database. When adding a new commodity or modifying or deleting commodities, the system needs to synchronize the data with memory. 2. When the user views the goods, firstly the system will check whether the goods have exceeded the end time or when the goods reach at the end time. The system uses Ajax technology to trigger the order generating program. The advantage of this scheme is easy to achieve. The disadvantage is that order information is not generated in real-time. Considering that there is no statistical function in this project, so we chose the second scheme | Michael
2020-04-14 | 9:30am~11:30pm | Do research Develop the user login and logout function | Do research for system analysis and design Develop the user login and logout function 1. The original plan is to continue to develop the auction function today, but the system must record user information before bidding. Therefore, the user management function is developed in advance. 2. Cong didn't use a cookie in the login function. in other words, the user must type the user name and password, when they log in the system. 3. If the user does not do anything in 15 minutes, the user needs to log in again | Michael
2020-04-15 | 9:30am~11:30pm | Modify prototype Develop the auction function. | Modify prototype (add bid history and shopping cart) Keep coding the auction function. the main job of today is when the commodities reach at the end time, the system uses AJAX to call order generation program. | Michael
2020-04-16 | 9:30am~11:30pm | System analysis and design Develop the user register and password recover function | Prepare system analysis and design When a user registers, the user name can not be repeated with the database. if the user name has already been taken, the system will prompt the error message. Password recover function needs the user to type a correct email address or mobile number. If the password or email address is correct, the user can change the password by themselves. | Michael
2020-04-17 | 9:30am~11:30pm | System analysis and design Develop personal profile. | Prepare system analysis and design Registered members can check or update their personal information except for the user name | Michael
2020-04-18 | 9:30am~11:30pm | Team meeting Documentation | Disscuss how to adjust the layout of the mainpage. Prepare meeting agenda and meeting minutes. | Michael
2020-04-20 | 9:30am~11:30pm | Advisor meeting Develop order management and make an appointment | Advisor meeting with Ian Report the progress with advisor and let him help us review proposal. Advisor Ian gave us a lot of suggestions for the proposal document. Normal users can only see their orders For customers, they can make an online appointment for pick-up and leave a message after they win the auction. It should be noted that the appointment time must be later than the current time. | Michael
2020-04-21 | 9:30am~11:30pm | Proposal document Develop the cart function | Modify the final version of the proposal document Do methodology research and add references. Imitating the function of the Trade me, user can add concerned commodities into the cart. If the user auctioned a commodity, the commodity will be automatically added to the shopping cart. In addition, when adding a commodity to the shopping cart, the system should check whether the goods are already in the shopping cart. If it already exists in the cart, Adding is not allowed. | Michael
2020-04-22 | 9:30am~11:30pm | System analysis and design Develop cart management function | Prepare the system analysis and design document. Users can delete items that they no longer concerned in their shopping cart. The implementation of the code is to set a delete state of the commodity rather than to delete the data from the database. | Michael
2020-04-23 | 9:30am~11:30pm | Proposal document System analysis and design Develop commodity management | Prepare system analysis and design document. Modify the final version of the proposal document. Add SWOT at the end of the methodology. Use a new template for the management side. The download address of the template is: http://www.cssmoban.com/cssthemes/9300.shtml 1. Separate the menu into a separate JSP file 2. The imported CSS conflicts with the original template. Merge the public content. | Michael
2020-04-24 | 9:30am~11:30pm | System analysis and design Develop adding a new commodity | Prepare the system analysis and design document. Develop add a commodity function. The difficulty is uploading pictures. should be noticed that The form format in the page is: enctype = "multipart / form-data" In Servlet, the method of parsing form is different from other Servlets. the system judges the uploaded file, it only supports common image formats. Images uploaded by the system will be renamed. To avoid repetition, to use UUID to get random names. The disadvantage of this method is that it can't be classified by file name. | Michael
2020-04-25 | 9:30am~11:30pm | Team meeting Documentation | Disscuss how to add map on the page of contact us. Prepare meeting agenda and meeting minutes. | Michael
2020-04-27 | 9:30am~11:30pm | Advisor meeting Develop the commodity management | Advisor meeting with Ian and modify two meeting minutes 1 only admin user can modify the commodity information 2. When a commodity has already bid by someone, the starting price cannot be modified 3. If did no select a new picture when modifying the commodity the old picture shall be used. 4. After the status of a commodity is changed to delete, the commodity will not be displayed on the store page. | Michael
2020-04-28 | 9:30am~11:30pm | System analysis and design Develop the user management | Modify the system analysis and design document Develop the user management | Michael
2020-04-29 | 9:30am~11:30pm | The function of about us Develop the user management | Search photos for the function of about us. I downloaded some pics to decorate the page. Develop the function to modify user status. There are two types of user states. 1. The admin user can set the user to disable. When it is set to disable, the user can no longer log in to the system for any operation. 2. Admin user can set normal users to admin. The admin user role cannot be registered. Only authorized by the admin user. | Michael
2020-04-30 | 9:30am~11:30pm | Prepare the introduction for the function of about us Develop the order management | Do research to understand the charity background, and write the introduction for the function of about us. Admin user can see all of the orders. This display page, to use the same page as my personal order page. The admin user can change the status of the order. When the status changes to picked up, the whole business process will end. | Michael
2020-05-01 | 9:30am~11:30pm | Mid project presentation Develop the order management | Prepare mid project presentation document according to supervisor's demands. I prepare to write it in 6 parts: cover, project purpose, project risk, Gantt chart, the solutions to project risk and deliverable list. Using different colours to distinguish the status of orders. Users can view auction bid history information through page Jump | Michael
2020-05-02 | 9:30am~11:30pm | Team meeting Documentation | Team meeting with teammate (Discuss development issue on goods management) Disscuss how to solve the problem of database timezone. Prepare meeting agenda and meeting minutes. | Michael
2020-05-04 | 9:30am~11:30pm | Advisor meeting Page beautification | Advisor meeting with Ian to report the progress of the project. Replace the advertising page and system logo. Unify the system icons Check the page for spelling errors correct the displayed information of the store bottom page. Add commodity search function on the main page. | Michael
2020-05-05 | 9:30am~11:30pm | Disscuss problem on goods management Page beautification | Discuss development on goods management. Administrator cannot delete items if the auction starts. Check all prompt information and alert message. Permission validation to ensure that each servlet validates session state. Using JavaScript and HTML5 new characteristic verifies the inputs.such as limit the type, length of the input. Required .etc. | Michael
2020-05-06 | 9:30am~11:30pm | System analysis and design Page beautification | Modify system analysis and design Maintain the contents of all error prompts and message reminders Adjust the bidding function of the auction. | Michael
2020-05-07 | 9:30am~11:30pm | Mid project presentation Add about us page and contact us page | Modify the powerpoint document (Add the previous Gantt chart to compare the current one) Use iframe to show Google maps. There is a third party on the Internet to provide Google location information services. After type specific location information, the URL with address information will be automatically generated, | Michael
2020-05-08 | 9:30am~11:30pm | Mid project presentation | Practise to show the presentation. | Michael
2020-05-09 | 9:30am~11:30pm | Team meeting Documentation | Project meeting with teammate (Discuss development issue on about us) Practise to show the presentation with teammate. Prepare meeting agenda and meeting minutes. | Michael
2020-05-11 | 9:30am~11:30pm | Advisor meeting Documentation | Advisor meeting with Ian Prepare milestone report for milestone1 (proposal phase) and milestone 2 (system design phase) | Michael
2020-05-12 | 9:30am~11:30pm | Mid project presentation | Show the presentation to supervisor Robert and answer his questions. 1.Q: What methodology did you use? A: Prototyping methodology. 2.Q: Why does your product use the auction function? A: Because the store is running the auction activity and it is the client’s requirement. The second-hand store is special. One stuff just one, so it is not suitable for the store to post everything online. 3.Q: What does your product bring to customers? A: It is easier for customers to buy something online and improve user shopping experience. | Michael
2020-05-13 | 9:30am~11:30pm | Test plan Code review | Modify test plan. Update schedule list. Optimizing code Delete all unused variables Formatting code Delete annotated code | Michael
2020-05-14 | 9:30am~11:30pm | Prepare test environment | Prepare test environment Install Tomcat Test to run the software package successfully. | Michael
2020-05-15 | 9:30am~11:30pm | Integration testing | Integration testing and record bugs or defects in the test case document. | Michael
2020-05-16 | 9:30am~11:30pm | Team meeting Documentation | Project meeting with teammate (Discuss how to modify system testing case) Discuss how to fix the bugs from the integration testing. Prepare meeting agenda and meeting minutes. | Michael
2020-05-18 | 9:30am~11:30pm | Advisor meeting Documentation Bug fix | Advisor meeting with Ian to report the progress of the project. Prepare milestone report for milestone3 (development phase) Depend on the results of the integration test, Cong fixed defects. The most common mistake is the spelling of upper and lower case. The most serious problem is the date input. The auction date cannot be displayed. Add a commodity function and make an appointment function cannot input date information, resulting in system errors. The result of the research is that the date input of HTML 5 could not support safari. The solution is to import a new date product. The download address is：https://www.layui.com/laydate/?alone | Michael
2020-05-19 | 9:30am~11:30pm | Integration testing report System testing | Prepare integration testing report. The purpose and statistic chart should be included. Start the system testing | Michael
2020-05-20 | 9:30am~11:30pm | Integration testing report System testing report Bug fix | Verify if the bugs have been fixed from the integration testing. Update the integration testing report. Prepare the system testing report. Fix the defects of the system test. Optimize page-turning query function | Michael
2020-05-21 | 9:30am~11:30pm | Prepare user manual prepare training document System testing report | Prepare user manual prepare training document Verify if the bugs have been fixed from the system testing. Update the system testing report. | Michael
2020-05-22 | 9:30am~11:30pm | Client meeting Set up test environment for the client Client training | Project meeting with the client. Set up test environment for the client The team give the client a training to help her understand how to use the system and how to execute the user acceptance testing. | Michael
2020-05-23 | 9:30am~11:30pm | Team meeting Documentation | Project meeting with teammate (Discuss something about the client handover) Prepare meeting agenda and meeting minutes. | Michael
2020-05-25 | 9:30am~11:30pm | Advisor meeting Documentation | Advisor meeting with Ian to report the progress of the project and discuss the client handover. Prepare milestone report for milestone4 (testing phase) | Michael
2020-05-26 | 9:30am~11:30pm | Prepare project closure report Write the installation manual | Prepare project closure report. Write the install manual. 1. the installation JDK manual 2.the installation MySQL database manual 3.the installation Tomcat manual Provide verification method after installation Prepare database initialization scripts. | Michael
2020-05-27 | 9:30am~11:30pm | Project closure report Client receipt and Client acceptance document Prepare resources for go-live | Prepare project closure report Prepare client receipt and client acceptance document Package all required resources Simulate the installation and deployment in the test environment. Verify whether the go-live environment is available, including product version | Michael
2020-05-28 | 9:30am~11:30pm | Prepare 1 page project handbook Modify project closure report | Prepare 1 page project handbook Modify project closure report | Michael
2020-05-29 | 9:30am~11:30pm | Go live Client handover | Go live and client handover The team has completed the client handover of all related documents and project code. | Michael
2020-05-30 | 9:30am~11:30pm | Team meeting Academic handover | Project meeting with teammate (Discuss the academic handover) Prepare the related documents for the academic handover | Michael
2020-05-31 | 9:30am~11:30pm | Academic handover | Prepare the related documents for the academic handover | Michael
2020-06-01 | 9:30am~11:30pm | Advisor meeting Documentation | Advisor meeting with Ian to report the progress of the project and discuss the academic handover. Prepare milestone report for milestone5 (client handover phase) | Michael
2020-06-02 | 9:30am~11:30pm | Academic handover | Prepare and update the related documents for the academic handover | Michael
2020-06-03 | 9:30am~11:30pm | Academic handover | Prepare and update the related documents for the academic handover | Michael
2020-06-04 | 9:30am~11:30pm | Academic handover | Prepare and update the related documents for the academic handover | Michael
2020-06-05 | 9:30am~11:30pm | Academic handover | Prepare and update the related documents for the academic handover | Michael
2020-06-06 | 9:30am~11:30pm | Team meeting Academic handover | Prepare and update the related documents for the academic handover | Michael
2020-06-07 | 9:30am~11:30pm | Academic handover | Prepare and update the related documents for the academic handover | Michael